## 16-06-2017
Module | Screens/Field | Issue Description | Critical | Status | Update date | Comments
Registration |  | After clicking submit button not geting any sms to mobile | High | open | 16-062017 | sms gateway is down
Registration | Membership ID | Membership Id takeing duplicate numbers | High | closed | 16-062017
Registration | Id Proof | if you select any id proof but with out entering id proof number details,it is submited | Low | closed | 16-062017
My profile |  | on clicking update button 1.use can't see any update and all fields are remain same as before update | Medium | closed | 16-062017
MemberLogin | MemberLogin Button | only entering username and click on submit button than not getting pop message like "password required" | Low | closed | 16-062017
Myprofile |  | Updated values are reflected in the my profile | Critical | closed | 16-062017

## 21-07-2017
Module | Screens/Field | Issue Description | Critical | Status | Remarks
Registration | Assembly,Mandal | if selecting any one option in Parliament dropdown list then next dropdown select option id disabled | high | closed
Registration | Mobile number | should not start with 0,1,2,3,4,5,6. | high | need to discuss
Registration | Assembly,Mandal,Parliament | In registration page without selecting parliament , the assembly should not be enabled, applicable for all location drop downs | high | closed
Registration |  | after click on submit not getting any confirmation message for mobile | low | sms server down
Registration | TollfreeNO | while calling to tollfree number , message is not receiving | high | need to discuss
Registration | Voter id | Field length should limit to 10 characters, whereas its accepting less than 10 characters. | low | closed
MyProfile | Confirm Voter ID | After entering the same details of voterid but it shows "VoterId Number Mismatch" error | low | closed
MyProfile | Id Proof | if we don’t select any dropdown of id proof but it showing Confirm voter ID Field | low | closed
Change Mobile Number |  | After entering all details in this screen,click on update button then pop messge is not proper…. Expected:Membership id already registerd | high | reopen
Home Screen | Member Login | after changing the Mobile Number,while logging again into app by new mobile number , it's not working by giving a message " invalid username/password" | high | fixed
Home | Registration | No action performed when tapping on "Choose File" button | low | fixed | not working below 4.01 android version
Network |  | No network is not handled. When there is no network proper error message should be shown | low | closed

## 22-07-2017
Module | Screens/Field | Issue Description | Critical | Status
MyProfile | Village | village dropdown field is not reflecting from Joint Booth Committee | high | closed
change mobile number | change mobile number | on clicking update button we are getting only username confirmation message expected: password also | high | closed
Registeration | Registeration | on clicking submit button its take long time for loading. | medium | closed

## 17-08-2017
web testing
Module | Screens/Field | Issue Description | Critical | Status
Registriation | voterid | voterid mismatch validation should not shown when user giving the correct id | low | reopen
my profile | voterid | voterid mismatch validation should not shown when user giving the correct id | low | reopen
change password | change password | after changing the password but here taking old password | high | closed
change password | new password | should not accept less then 6 digits | high | open

## 04-08-2017
web testing
Module | Screens/Field | Issue Description | Critical | Status
Myprofile | Graduate | after loging -->graduate field not showing | closed | open
Myprofile | voterid | after clicking update button voterid is not updating | closed | open
Myprofile | confirmvoterid | confirm voterid is not showing in my profile screen | closed | open
change password | change password | after changing the password but here taking old password | closed | open

## 15-06-2017
Sno | Module | Screens/Field | Issue Description | Critical | Status | Comments
1 | Registration | ID Proof Number | ID Proof Number is taking more then 12 digits | Medium | closed
2 | Registration | BoothNumber | generated Booth Number is should be Right Aligned | Low | closed
3 | ForgotPassword | submit button | User should be restricted to single click on submit button | Medium | closed
4 | ForgotPassword | submit button | After clicking on submit button it takes more time to show the updated password | Medium | closed | loading bar is placed
5 | MyProfile | DOB | blank popup is shown when tapping on DOB date picker | High | closed
6 | Change Password |  | Passwords entered should be masked with * for below fields Current Password New Password Confirm Password | High | closed | need to discuss

## 14-06-2017
Module | Screens/Field | Issue Description | Critical | Status
Menu | Menu (Sub Modules) | Modules are missing, where in last build we have some sub modules 1.News 2.Home 3.Login etc.. | Medium | closed
Registration | Name&Surname | Accepting numbers for Name and Surname | High | closed
Registration | Name | In the name field spaces are not accepting | Medium | closed
Registration |  | when we write any field and when we click the enter button the date format is displaying | High | closed
Myprofile | Id proof | Myprofile id proof accepting more than 12 digits | Medium | closed
Myprofile |  | My profile Update button not working | Medium | closed
Home-in Screen |  | change the name of MyAccount to MyProfile | Medium | closed
Home-in Screen |  | when we click on report button it is redirecting to change password screen | High | closed
Myprofile |  | In DOB , month is not changing | High | closed
Myprofile |  | After entering valid data and when we click submit again it is showing validations | High | closed
Registration
Registration | DOB | date picker age is taken below 18 years | High | closed
Registration | Booth Number | Booth Number generated should not be editable in Registration screen | Low | closed
Home screen |  | No action performed choose file button in samsung tablet | High | closed
Registration | MemberLogin | Member login button is not working | High | closed
Myprofile |  | In DOB Sunday day not is visible | Medium | closed
Myprofile |  | Unable to edit DOB | High | closed
Myprofile |  | membership id shouldn't be editable | High | closed
Myprofile |  | Able to click update button multiple times so multiple confirmation popups are showing | Medium | closed
Home |  | Updated values are reflected in the my profile | Critical | closed
Login | News | On tapping news navigating to blank screen, but for logged in user news button is not working | Medium | closed
|  | Tap on login from humburger menu-login to app-click on back application back button-app navigates to login screen | High | closed

## 12-06-2017
Module | Screens/Field | Issue Description | Critical | Status
Login |  | Exit application should be as mentioned in the screenshot Exit CMS(popup header) Are you sure you want to exit CMS? Cancel and Ok Buttons | Medium | Closed
Login |  | User name should be renamed to Username |  | closed
Login | Join BJP | Login Screen-Join BJP->App should navigate to registration screen on tapping Join BJP whereas app is navigating to Home screen |  | closed
Login |  | Humburger menu is not available in Login screen |  | closed
Network |  | No network is not handled. When there is no network proper error message should be shown | Low | open
Exit |  | "are you sure you want to exit?" popsup in all screens while tapping on device back key. Expected: App should navigate back. If the user clicks back from home screen/login screen such popup should be prompted | High | closed
Home Screen | News | No action performed when tapping on "News" button |  | Closed
Registration | DOB | Unable to scroll Year and Month in Date picker | High | closed
| DOB | Unable to swipe month in the Date picker to change the month | High | closed
| DOB | Unable to change the date using the Date picker | High | closed
| DOB | Application taking around 5 seconds to open DatePicker | High | closed
| Membership Id | By default Numeric keyboard should be shown for better user experience | Low | closed
| Upload Photo | No action performed when tapping on "Choose File" button | High | closed | above os version 5 it will be worked
| Submit | No action performed when tapping on "Choose File" button, unable to Register | Critical | Closed
| ID Proof Number | Field length should limit to 12 characters, whereas its accepting more than 12 characters. |  | closed
Menu | Menu (Sub Modules) | Modules are missing, where in last build we have some sub modules 1.News 2.Home 3.Login etc.. | Medium | closed

## 21-08-2017
web testing
Module | Screens/Field | url link | Issue Description | Critical | Status
Login | user login | http://202.153.34.166:8001/accounts/login/ | username should accept 10 digits | high | closed
Login | user login | http://202.153.34.166:8001/accounts/login/ | password should not accept less then 6 digits | high | closed
Membership | membership roles | http://202.153.34.166:8001/accounts/membershiprole/ | newmembership role -> on selecting view other options disabled after saving | high | closed
Membership | membership roles | http://202.153.34.166:8001/accounts/membershiprole/ | newmembership role -> on selecting edit other options disabled after saving | high | closed
Membership | membership roles | http://202.153.34.166:8001/accounts/membershiprole/ | no confirmation messages for delete | high | closed
Membership | membership approvles | http://202.153.34.166:8001/accounts/membership/approvals | after approving the recommendation role should not change | high | closed
Membership | membership | http://202.153.34.166:8001/ | after loging->it showing only bulckupload option when select the mandal approverole | high | closed
Membership | recommendation,registeration,membershiprole,aprovals | http://202.153.34.166:8001/accounts/membership/recommendations | no data should not show while deselcting the village | high | closed
Membership | recommendation,registeration,membershiprole,aprovals | http://202.153.34.166:8001/accounts/membership/recommendations | SelectBooth-->boothnumbers are not showing in assending order | medium | closed

## 23-08-2017
Module | Screens/Field | Issue Description | Critical | Status
Myprofile | Myprofile | update button is enabled when upmandal is deselected | high | fixed
Myprofile | Myprofile | clicking the update button it will take more time loading | high | fixed
registeration | Upmandal | submit button is enabled when upmandal is deselect option | high | fixed
registeration | Upmandal | No network is not handled. When there is no network proper error message should be shown | high | reopen
Myprofile | photo | in my profile screen photo field option is not eflecting from rgisteration | low | fixed
registeration | mandal | not showing records in mandal list | high | fixed

## 28-08-2017
SUPER ADMIN WEB TESTING
Module | Screens/Field | url link | Issue Description | Critical | Status | advice | Developer comments
Membership | Registiration | http://202.153.34.166:8001/accounts/membershipbulkupload/new | select booth dropdown id name is not visible in this screen | low | closed
Membership | Registiration | http://202.153.34.166:8001/accounts/membership/view/28 | if you click the close button its doesnot redirecting the page | low | closed
Membership | Registiration | http://202.153.34.166:8001/accounts/membership/registrations | Select Booth-->if you checking the booth data one by one then select booth dropdown is not selecting | high | closed
help | help | http://202.153.34.166:8001/accounts/membership/registrations | help option is not working | high | Need Clarification
membership | Registiration | http://202.153.34.166:8001/accounts/membership/registrations | in registeration page deselect the village dropdown list but it shows the booth data | high | closed
membership | Registiration,recommendation | http://202.153.34.166:8001/accounts/membership/registrations | deselect the mandal,assembly options but it doesnot showing the mandal,assembly options | high | closed
membership | Registiration,recommendation | http://202.153.34.166:8001/accounts/membership/recommendations | in registeration page booth drop down showing the booth data and recommendation page booth option showing the booth numbers | medium | closed
Login | user login | http://202.153.34.166:8001/accounts/login/ | username should accept 10 digits | high | Need Clarification
Login | user login | http://202.153.34.166:8001/accounts/login/ | password should not accept less then 6 digits | high | Need Clarification
Membership | membership roles | http://202.153.34.166:8001/accounts/membershiprole/ | newmembership role -> on selecting view other options disabled after saving | high | it is not a bug please keep it is an suggestion
Membership | membership roles | http://202.153.34.166:8001/accounts/membershiprole/ | newmembership role -> on selecting edit other options disabled after saving | high | it is not a bug please keep it is an suggestion
Membership | membership roles | http://202.153.34.166:8001/accounts/membershiprole/ | no confirmation messages for delete | high | closed
Membership | membership approvles | http://202.153.34.166:8001/accounts/membership/approvals | after approving the recommendation role should not change | high | phase 2
Membership | membership | http://202.153.34.166:8001/ | after loging->it showing only bulckupload option when select the mandal approverole | high | closed
Membership | recommendation,registeration,membershiprole,aprovals | http://202.153.34.166:8001/accounts/membership/recommendations | data should not shown, if deselcting the village | low | reopen
Membership | recommendation,registeration,membershiprole,aprovals | http://202.153.34.166:8001/accounts/membership/recommendations | SelectBooth-->boothnumbers are not showing in assending order | medium | closed
|  | http://202.153.34.166:8001/accounts/membership/recommendations | page is not refreshing in every time | medium | reopen
Membership | bulckupload->choose file | http://202.153.34.166:8001/accounts/membershipbulkupload/new | choose file---> if you select any wrong file it goes into the initial page | medium | fixed |  | load performance issue
home | forgot password | http://202.153.34.166:8001/welcome/#/side-menu21/forgotpassword | after clicking forgot password it should not redirect into super admin page | medium | re open
Membership | approval | http://202.153.34.166:8001/accounts/membership/approvals | should be add edit option in this case | medium | Phase 2
Membership | registeration | http://202.153.34.166:8001/accounts/membership/registrations | after login the approved person Select Booth-->if you checking the booth data one by one then select booth dropdown is not selecting | high | closed
Membership | approval | http://202.153.34.166:8001/accounts/membership/approvals | membership-->approval-->if select a approved person has a booth president we don’t get confirmation message properly | medium | closed
Myaccount | changepassword | http://202.153.34.166:8001/accounts/changepassword/ | newpassword--> should not accept password less then 6 digits | medium | reopen
Membership | membership premissions | http://202.153.34.166:8001/accounts/membershiprolepermissions/ | spaces are not there in header names-->member ship recommendations,parlimentry | low | closed
home |  |  |  | medium | open | should not show previous page
home | [5 empty] | date and time should be in proper manner
Dashboard | Dashboard | http://202.153.34.166:8001/campaign/dashboard |  |  |  | here we should mentioned A,B,C,D Represents
Membership | membership roles,recommendations,locations | http://202.153.34.166:8001/accounts/membershiprolepermissions/ | if click the delete option we get confirmation message is not properly | medium | closed
Locations | parliments | http://202.153.34.166:8001/campaign/locations | edit-->if click the close option should not goes into intial page | medium | fixed |  | load performance issue
Locations | parliments | http://202.153.34.166:8001/campaign/locations | view-->close-->if click the close option should not goes into intial page | medium | fixed |  | load performance issue
Locations | delete | http://202.153.34.166:8001/campaign/locations57330/delete | delete option is not working | high | closed
Locations | Location form | http://202.153.34.166:8001/campaign/locations/new | eg:If we select hierachry level option is assembly but parent option is showing total hierachry | medium | closed
Locations | Location form | http://202.153.34.166:8001/campaign/locations | search option also not working | medium | closed
Locations | Location form | http://202.153.34.166:8001/campaign/district/ | click the delete option,confirmation message is not properly | medium | closed
Locations | District | http://202.153.34.166:8001/campaign/district/new | Zone-->zone dropdown list showing only "kadapa" | medium | closed
Locations | Hierachray level | http://202.153.34.166:8001/campaign/hierarchylevels11/delete | delete option is not working | high | closed
Locations | Hierachray level | http://202.153.34.166:8001/campaign/hierarchylevels/new | delete option is not working | high | closed
Locations | Location Transform | http://202.153.34.166:8001/campaign/locations/transform | Location Trans form is not working | high | closed
Locations | District,Zone | http://202.153.34.166:8001/campaign/locations/transform | should not accept numbers | high | closed
Campigin | Campigin type | http://202.153.34.166:8001/campaign/campaigns | should not accept numbers | high | closed
Campigin | Campigin type | http://202.153.34.166:8001/campaign/types | should not accept numbers | high | closed
settings | mobileapk | http://202.153.34.166:8001/accounts/mobileapk | should accept only apk extensions | high | closed

## 1-09-2017
Module | Screens/Field | url link | Issue Description | Critical | Status | advice | devloper comments
Membership | bulckupload | http://202.153.34.166:8001/accounts/membershipbulkupload/new | in parliment page deselect the village dropdown list but it doesnot showing the booth data | high | closed
events | events | http://202.153.34.166:8001/ | in home page events are should not publishing | high | closed
locations | districts | http://202.153.34.166:8001/campaign/zone/ | Locations -->districts--> records are not updating | high | closed
locations | HierarchyLevel Form | http://202.153.34.166:8001/campaign/hierarchylevels/new | with out selecting the parent dropdown list records are saved | medium | reopen
locations | Transform | http://202.153.34.166:8001/campaign/locations/transform | clciking on submit button--> we get a popmessge but with out touching close button, its sudennly vanished | medium | reopen |  | For this we mentioned some timestamp to close automatically.
membership | bulckupload | http://202.153.34.166:8001/accounts/membershipbulkupload | when we refresh in third page its should not go into first page | low | open |  | Need Clarification
membership | bulckupload | http://202.153.34.166:8001/accounts/membershipbulkupload | in caste column should not accepting spaces | high | closed
locations | parliments | http://202.153.34.166:8001/locations/Parliments | if click on edit option,should not reflecting the data of "select parlimentry" dropdown. | high | reopen
campgin | campign types | http://202.153.34.166:8001/campaign/types | delete option is not working | high | closed
campign | campigns | http://202.153.34.166:8001/campaign/campaigns | delete option is not working | high | closed
locations | parliments | http://202.153.34.166:8001/campaign/locations | should not showing the data when deselect the mandal,upmandal,village | high | reopen
locations | Districts | http://202.153.34.166:8001/campaign/district/ | delete option is not working | high | closed
membeship | membership bulckupload | http://202.153.34.166:8001/accounts/membershipbulkupload | after uploading the bulckupload excel sheet-->should not showing the status | high | closed

## 29-08-2017
MOBILE AND WEBPOTRAL TESTING
Module | Screens/Field | Issue Description | Critical | Status
Myprofile&registiration | name and surname | it showing underline below name and surname | high | closed
Myprofile | change new password | after changing the password , it showing the validations | medium | closed

## 14-09-2017
Module | Screens/Field | url link | Issue Description | Critical | Status | advice | developer comments
settings | sms gateway,mobileapk,events,idproofs,usercategories | http://202.153.34.166:8001/accounts/smsnew | unnecessary buttons are there in setting dropdown total feature | high | closed
campaign | campaign | http://202.153.34.166:8001/campaign/new | click on save --> campign name already register error message should not be shown when user update the details | high | closed
Membership | bulckupload | http://202.153.34.166:8001/accounts/membershipbulkupload/new | choose file--> "MembershipBulkUpload with this Name already exists" error message does not reset when deselect the dropdown list | high | reopen
Membership | bulckupload | http://202.153.34.166:8001/accounts/membershipbulkupload/new | choose file--> "MembershipBulkUpload with this Name already exists". error message should not shown,if user selecting the same file name | high | reopen
home |  | http://202.153.34.166:8001/accounts/login/ | refresh button is not working properly --.>when click on login button, without enterning the credentails | medium | reopen
home | username | http://202.153.34.166:8001/accounts/login/ | in the username field spaces should accept but it is not accepting | medium | reopen
Location form | Lattitude | http://202.153.34.166:8001/campaign/locations/57332/edit | validation should not be shown,if user clciking on save button for lattitude | medium | reopen

## 28-09-2017
Module | Screens/Field | url link | Issue Description | Critical | Status
Home | Home | http://202.153.34.166:8001/ | if approved person loginig(select a assembly data manager)--> its should not show bulckupload feature | high | closed
Home | Home | http://202.153.34.166:8001/ | if approved person loginig(select Mandal as a assembly data manager)--> its should not show bulckupload feature | high | reopen
membership | recommendation | http://202.153.34.166:8001/accounts/membership/recommendations | should be category column name changes to caste | low | open
Membership | bulckupload | http://202.153.34.166:8001/accounts/membershipbulkupload | recently records are not showing first | low | open
Location | transform | http://202.153.34.166:8001/campaign/locations/transform | should be write validation for every location ,while moving the locations transform from one area to another area | high | open
membership | recommendation,approval | http://202.153.34.166:8001/accounts/membership/recommendations | should be add one more column in this field(Mobile number) | high | open

## 18-09-2017
Module | Screens/Field | url link | Issue Description | Critical | Status | advice | comments
Membership | Registeration--> Booth | http://202.153.34.166:8001/accounts/membership/registrations | booth number is not reflecting from excel sheet | high | closed
Membership | bulckupload--> voterid |  | voter-id : "Invalid Vote Id "error message should not be shown when user giving valid voterid | high | closed
bulckupload | Assembly code |  | other assembely codes are should not accepting | high | closed
bulckupload | Assembly code & booth code |  | system_errors : ('Error on line 61', 'AttributeError', AttributeError("'int' object has no attribute 'isdigit'",)), error message should be shown if assembly & booth field left. | high | closed
bulckupload | Name | http://202.153.34.166:8001/accounts/membershipbulkupload/booth | "file name already register" error message should be shown when user selecting already file name. | high | reopen
Membership | registirations-->booth | http://202.153.34.166:8001/accounts/membership/registrations | in booth column its showing asssembly code, it should show booth code | high | closed
Membership | bulckupload | http://202.153.34.166:8001/accounts/membership/registrations | bulckupload-->booth --> its not working | high | closed

## 06-10-2017
WEB APP TESTING REPORT
Module | Screens/Field | Issue Description | Critical | Status | advice | user comments
Myprofile | photo | photo option is not refelcting from join booth committee | high | reopen
Myprofile | update button | after changing the membership id,click on update button it will take more time | high | closed
Myprofile | voterid | invalid voterid message should be shown when user giving correct voterid | high | closed
myprofile | voterid | if we change any field in my profile then click on update button "invaild voterid " message shown | high | closed
Myprofile | pincode | should not be accepting alphabets,special charcters | high | closed
Myprofile | pincode,door no,street | should be aligin in right side | high | closed
REGISTERATION,MYPROFILE | MOBILE NUMBER | should be start from 7,8,9 only | high | closed
REGISTERATION | submit | click on submit button it it will take more time | high | closed
registeration,myprofile | pincode | pin code pop message should be change asa "Invalid PIN Code" | medium | closed
Myprofile | pincode | should accept only numbers but its accepting others "---" | high | closed
Myprofile | Change password | its showing validation error message,page is not refreshing | medium | closed

## 6-10-2017
MOBILE APK TESTING
Module | Screens/Field | Issue Description | Critical | Status | advice
Registeration | door no | numeric keyboard showing only numbers | high | closed
Registeration | street | numeric keyboard showing only numbers | high | closed
Registeration | submit | on tapping submit button no action is performed | high | closed
Myprofile | photo | photo option is not refelcting from join booth committee | high | reopen
Myprofile | photo | photo field is not updateing | high | reopen
Regi,Myprofile | pincode | pincode name should be changed as a"PIN Code" | high | closed
registeration,myprofile | voterid | voter id required validation should be change as a "Enter Valid voter id" | high | closed
login | forgot password | page is not reset | medium | closed
registeration,myprofile | pincode | should accept only numbers | high | closed
registeration,myprofile | pincode | pin code pop message should be change asa "Invalid PIN Code" | medium | closed
Myprofile | pincode | should accept only numbers but its accepting others "---" | high | closed

## 12-10-2017
CMS ADMIN POTRAL TESTING REPORT OF REPORTS FEATURE
Module | Screens/Field | url link | Issue Description | Critical | Status | comments
Reports | Action | http://202.153.34.166:8001/accounts/membership/reports | After logging into a profile without any approval while its showing booth leader | high | closed
Reports | view | http://202.153.34.166:8001/accounts/membership/view/22 | click on view button then id proof name should be change as a voter id | high | closed
Reports | caste, graduate,age | http://202.153.34.166:8001/accounts/membership/reports | with out select any option in filter then click on submit button its does not show previous data(N/A) | high | closed
Reports | FILTER | http://202.153.34.166:8001/accounts/membership/reports | page is not reset in filter | high | closed | not a issue
Reports | age | http://202.153.34.166:8001/accounts/membership/reports | keep it as max age should be 100 | low | closed
Reports | Download | http://202.153.34.166:8001/accounts/membership/reports | before filter clcik on download button its showing empty excel data sheet | high | closed
membership | Download | http://202.153.34.166:8001/accounts/membership/export?location_id=24463 | clcik on download button its showing error meassage | high | closed
MyAcoount | ViewProfile | http://202.153.34.166:8001/accounts/profile/view | After logging into a profile,click on "VIEW PROFILE" button then id proof field name should be change as a "Voter id" | high | open

## 26-10-2017
CMS WEB TESTING REPORT
Module | Screens/Field | url link | Issue Description | Critical | Status | comments
Bulck registeration | voter-id | http://202.153.34.166:8001/accounts/membershipbulkupload | should not be accept spaces in the middle of voterid | high | Closed
Bulck registeration | Caste | http://202.153.34.166:8001/accounts/membershipbulkupload | should not be accept spaces in the middle of caste field | high | Closed
Bulck registeration | gender | http://202.153.34.166:8001/accounts/membershipbulkupload | validation error message should be change, when user left the field | high | Closed
Bulck registeration | booth code | http://202.153.34.166:8001/accounts/membershipbulkupload | validation message should not be shown | high | Closed

## 27-10-2017
MOBILE APK TESTING AND 202 WELCOME PAGE OF NEW FEATURES
Module | Screens/Field | Issue Description | Critical | Status | developer comments
Myprfoile | email | 1) Should not be Leading dot in email is not allowed example: ".email@gmail.com". 2)should not be Trailing dot in email is not allowed example: "email.@gmail.com". 3)should not allowed Multiple dots example: "email..email@gmail.com" 4)Missing top level gmail (.com/.net/.org/etc) example: "email@gmail" 5) .web is not a valid top level domain example: "email@gmail.web". Allows only(.com/.net/.org/etc) 6)Invalid IP format not alloewed example: "email@111.222.333.44444" | high | closed
Feedback | submit | after click on submit button page is not redirecting | high | open
Registeration | email | showing same myprofile errors of email field in registeration of email field also. | high | closed
MYprfoile | Download id card | download id card name should be change as a meaning full name | high | open
Download id card |  | alignments are not in proper order, So should be arrange in order village,booth,assembly | high | open
News | News | news button is not working | high | open
Mobilenumber |  | should not accept same number in total field | high | closed
Home | News | In news page have a table format, | high | closed
login | submit | enter the credentaionals,click on submit button is not working | high | open

## 1-11-2017
CMS WEB TESTING REPORT OF NEW FEATURE AS ASSEMBLY LEVEL IN BULCKUPLOAD
Module | Screens/Field | url link | Issue Description | Critical | Status | Developer comments
Home | Home | http://202.153.34.166:8001/ | Campign dropdown feature misssing in home page | high | closed
Membership | GENDER | http://202.153.34.166:8001/accounts/membershipbulkupload/assembly | should not accept spaces in middle of gender | high | closed
Membership | DoorNumber | http://202.153.34.166:8001/accounts/membershipbulkupload/assembly | should not accept years in doornumber field | high | closed
Membership | email | http://202.153.34.166:8001/accounts/membershipbulkupload/assembly | should not accept spaces in the middle of email | high | closed
Membership | voter id | http://202.153.34.166:8001/accounts/membershipbulkupload/assembly | " invalid voter id" validation message "r" missing | high | closed
Membership | pincode | http://202.153.34.166:8001/accounts/membershipbulkupload/assembly | "pincode required validation "error message is showen, if mentioned pincode field as a optional | high | closed
Membership | email | http://202.153.34.166:8001/accounts/membershipbulkupload/assembly | should accept spaces | high | closed
Membership | mobile number | http://202.153.34.166:8001/accounts/membershipbulkupload/assembly | should not accept mobile number a same number as a "9999999999" | medium | closed
bulck registeration | Download templete | http://202.153.34.166:8001/accounts/membershipbulkupload/assembly | click on teplete button "AC AND BC" filed have in middle of excel sheet,hence after uploading the excel "AC AND BC" fields in last | medium | closed
mebership | email |  | should accept dots in the middle of email field | medium | closed
mebership | email |  | should accept dots in the middle of email field | medium | closed
mebership | email |  | Your username has to end with a letter or a number before "@" | medium | closed
mebership | email |  | should be allowed upper case letters after @ symbol in gmail | high | closed

## 8-11-2017
MOBILE APK TESTING AND 202 WELCOME PAGE OF NEW FEATURES
Module | Screens/Field | Issue Description | Critical | Status | developer comments
Registeration | email | Your username has to end with a letter or a number before "@" | high | closed
Registeration | email | should accept dots in the middle of email field | high | closed
Myprofile | email | Your username has to end with a letter or a number before "@" | high | closed
Myprofile | email | special characters should not allowed as first letter in email field | high | closed
Myprofile | download id card ---> Booth number | if not selected any data of booth number field in "my profile" but after downloading the id card its showing automatically booth number | high | closed
Myprofile | download id card ---> village | not reflecting village field data in Id card from "update profile" | high | closed
login | submit | csrf error showen click on submit button | high | reopen
Myprofile | update | update button is not working, its showing csrf error | high | reopen

## 22-11-2017
CMS WEB TESTING REPORT OF NEW FEATURE AS BOOTH LEVEL IN BULCKUPLOAD
Module | Screens/Field | url link | Issue Description | Critical | Status | Developer comments
Membership | email | http://202.153.34.166:8001/accounts/membershipbulkupload | should not accept spaces in the middle of email field | high | open